## Timeline
⏱ Timeline
One row per month (M1–M12). Set 'Is Current Month' = Yes for today's month.
Month Key | Calendar Label | Working Hours | Is Current Month
M1 | Mar-26 | 176 | No
M2 | Apr-26 | 176 | Yes
M3 | May-26 | 168 | No
M4 | Jun-26 | 176 | No
M5 | Jul-26 | 184 | No
M6 | Aug-26 | 168 | No
M7 | Sep-26 | 176 | No
M8 | Oct-26 | 176 | No
M9 | Nov-26 | 168 | No
M10 | Dec-26 | 184 | No
M11 | Jan-27 | 168 | No
M12 | Feb-27 | 160 | No

## Resources
👥 Resources
One row per person. POD, Role, Cap FTE, Location (US/India), Active (Yes/No) drive all capacity calculations.
Name | POD | Role | Cap FTE | Location | Active
Alice Chen | Portal V1 | Developer | 1 | US | Yes
Ravi Patel | Portal V2 | QA | 1 | India | Yes
Sara Kim | Integrations | BSA | 1 | US | Yes
Tom Bradley | Enterprise Systems | Tech Lead | 1 | US | Yes
Priya Sharma | Accessioning | Developer | 1 | India | Yes

## Availability
📅 Availability
Actual available hours per person per month. 176 = full month, 0 = absent. Must list every active resource.
Name | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27
Alice Chen | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Ravi Patel | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Sara Kim | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Tom Bradley | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Priya Sharma | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160

## POD Splits
🔀 POD Splits
Permanent = always split (e.g. 50% Epic / 50% Integrations). Temporary = short-term loan. Split% = fraction going TO the override POD (0.5 = 50%).
Name | Start Month | End Month | POD | Split% | Notes | Type
Tom Bradley | M1 | M12 | Integrations | 0.5 | 50% home POD + 50% Integrations | Permanent
Alice Chen | M3 | M5 | Portal V2 | 0.4 | Temporary support during Portal V2 launch | Temporary

## Assumptions
⚙️ Assumptions
Hours per FTE / Month = standard capacity basis. BAU % = maintenance time not available for project work.
Hours per FTE / Month | 160
POD | Role | BAU %
Portal V1 | Developer | 0.2
Portal V1 | QA | 0.25
Portal V1 | BSA | 0.15
Portal V1 | Tech Lead | 0.1
Portal V2 | Developer | 0.2
Portal V2 | QA | 0.25
Portal V2 | BSA | 0.15
Portal V2 | Tech Lead | 0.1
Integrations | Developer | 0.2
Integrations | QA | 0.25
Integrations | BSA | 0.15
Integrations | Tech Lead | 0.1

## Sizing
📐 Sizing & Complexity
T-shirt sizes → base hours. Mix% = role effort percentage (must sum to 100%). Complexity = POD multiplier applied to base hours.
Size | Base Hours | Role | Mix% | POD | Complexity
XS | 150 | Developer | 0.6 | Portal V1 | 1
S | 350 | QA | 0.2 | Portal V2 | 1
S+ | 600 | BSA | 0.1 | Integrations | 1.4
M | 1000 | Tech Lead | 0.1 | Accessioning | 1.2
M+ | 1800 |  |  | Epic | 1.1
L | 3000 |  |  | LIS/Reporting | 1.15
L+ | 5000 |  |  | Enterprise Systems | 1.05
XL | 8000

## Effort Patterns
📈 Effort Patterns
Relative weight per period (W1=M1 of project, W12=M12). Java normalises — no need to sum to 1. Zeroes after project end are safe.
Pattern Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Flat | bar: W1 to W12
Ramp Up | 0.5 | 0.7 | 0.9 | 1.1 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1
Ramp Down | 1.2 | 1.2 | 1.1 | 0.9 | 0.7 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
Up/Down | 0.7 | 0.9 | 1.1 | 1.2 | 1.1 | 0.9 | 0.7 | 0.5 | 1 | 1 | 1 | 1
QA Late Peak | 0.4 | 0.6 | 0.8 | 1 | 1.2 | 1.4 | 1.2 | 1 | 0.8 | 0.6 | 0.4 | 0.4
Dev Ramp | 0.6 | 0.8 | 1 | 1.1 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1
BSA Early | 1.6 | 1.4 | 1.2 | 1 | 0.8 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Tech Lead Light | 1.2 | 1.1 | 1 | 0.9 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Middle Spike | 0.1 | 0.2 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0
Spike + Stabilize | 0.3 | 0.25 | 0.15 | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
End Spike | 0.05 | 0.1 | 0.15 | 0.2 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Short 3m Up/Down | 0.6 | 1.2 | 0.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Projects
📁 Projects
One row per project. Status must be 'Active' for demand to be calculated. Start M / End M use M1–M12 keys from Timeline.
Name | Priority | Owner | Start M | End M | Duration | Pattern | Status | Launch Date | Notes | Required Skills
Portal V2 MVP | P0 | Digital Products | M1 | M3 | 3 | Flat | Active | May-26
VA PGx Integration | P1 | BD | M3 | M9 | 7 | Ramp Up | Active | Nov-26 | USVA | HL7
Digital Order Triage | P1 | S2C | M1 | M6 | 6 | Ramp Up | Active | Aug-26
Unified Test Catalog | P2 | S2C | M5 | M11 | 7 | Flat | Active | Jan-27

## POD Planning
🎯 POD Planning
One row per Project + POD. Start M blank = use project start. Duration blank = use project duration. Pattern overrides the project default.
Project | POD | Size | Complexity | Pattern | Start M | Duration
Portal V2 MVP | Portal V2 | XL | 1 | Flat | M1 | 3
VA PGx Integration | Integrations | XL | 1 | Ramp Up | M3 | 7
VA PGx Integration | LIS/Reporting | L | 1 | Ramp Up | M3 | 7
Digital Order Triage | Enterprise Systems | XL | 1 | Ramp Up | M1 | 6
Digital Order Triage | Portal V1 | L | 1 | Ramp Up | M1 | 6
Unified Test Catalog | Portal V1 | XL | 1 | Flat | M5 | 7
Unified Test Catalog | Portal V2 | L | 1 | Flat | M5 | 7

## Cost Rates
💲 Cost Rates
Hourly rates by role and location. Imported automatically — used for project cost estimates. Role must match exactly: Developer, QA, BSA, Tech Lead.
Role | US ($/hr) | India ($/hr)
Developer | 200 | 75
QA | 150 | 60
BSA | 175 | 70
Tech Lead | 225 | 90

## Skills
🏷 Skills
Tag each person with comma-separated skills (e.g. React, Python, AWS, HL7). Used for skill-gap analysis. Name must match the Resources sheet exactly.
Name | Skills (comma-separated)
Alice Chen | React, TypeScript, AWS
Ravi Patel | Selenium, JIRA, Postman
Sara Kim | HL7, FHIR, Business Analysis
Tom Bradley | Java, Spring Boot, Architecture
Priya Sharma | Python, React, Node.js

## Actuals
📊 Actuals
Hours actually logged per project per month — fill in after each month closes. Leave blank for future months. Project names must match the Projects sheet.
Project | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27
Portal V2 MVP | 320 | 280 | 310
VA PGx Integration |  |  | 240 | 320 | 380 | 400 | 370
Digital Order Triage | 180 | 200 | 240 | 280 | 300 | 310
Unified Test Catalog |  |  |  |  | 160 | 200