## Timeline
⏱ Timeline
One row per month. Change "Is Current Month" to Yes for the current month.
Month Key | Calendar Label | Working Hours | Is Current Month
M1 | Mar-26 | 176 | No
M2 | Apr-26 | 176 | Yes
M3 | May-26 | 168 | No
M4 | Jun-26 | 176 | No
M5 | Jul-26 | 184 | No
M6 | Aug-26 | 168 | No
M7 | Sep-26 | 176 | No
M8 | Oct-26 | 176 | No
M9 | Nov-26 | 168 | No
M10 | Dec-26 | 184 | No
M11 | Jan-27 | 168 | No
M12 | Feb-27 | 160 | No

## Resources
👥 Resources
One row per person. POD, Role, Cap FTE, Location, Active drive all capacity calculations.
Name | POD | Role | Cap FTE | Location | Active
Katy Zarty | Enterprise Systems | Developer | 1 | US | Yes
Kaitlyn E. Walton | Enterprise Systems | Developer | 1 | US | Yes
Justin Branch | Enterprise Systems | Developer | 1 | US | Yes
Priti Kothavale | Enterprise Systems | QA | 1 | US | Yes
Rowin W. Cordon | Enterprise Systems | Developer | 1 | US | Yes
Arnold Parge | Enterprise Systems | Tech Lead | 0.5 | India | Yes
Kamal Joshi | Enterprise Systems | Developer | 1 | India | Yes
Aastha Sahu | Enterprise Systems | Developer | 1 | India | Yes
Vrushali Kapadner | Enterprise Systems | QA | 1 | India | Yes
Tamika P. Jarmond | Enterprise Systems | BSA | 1 | US | Yes
Katrina Lee | Enterprise Systems | QA | 0.5 | US | Yes
David A. Buchanan | Epic | Developer | 1 | US | Yes
Yali Ren | Epic | Developer | 1 | US | Yes
Pamela Bowman | Epic | Developer | 1 | US | Yes
Yutaka Hitomi | Epic | Developer | 1 | US | Yes
Rayonia T. Slater-Smith | Epic | Developer | 1 | US | Yes
Greg J. Andresen | Epic | BSA | 0 | US | Yes
Amey Dodal | Accessioning | BSA | 1 | India | Yes
Hrishikesh Kadam | Accessioning | Developer | 1 | India | Yes
Gurneet Singh | Accessioning | BSA | 1 | US | Yes
Win T. Aung | Accessioning | Tech Lead | 0.5 | US | Yes
Subin K. Pillai | Accessioning | Tech Lead | 0.5 | US | Yes
Raviraj R. Ghare | Accessioning | Developer | 1 | India | Yes
Suraj Wankhade | Accessioning | Developer | 1 | India | Yes
Abhishek N. Bulbule | Accessioning | Developer | 1 | India | Yes
Srushti S. Raut | Accessioning | QA | 1 | India | Yes
Francisco J. Martinez | Accessioning | Developer | 1 | US | Yes
Sneha Patil | Accessioning | QA | 1 | India | Yes
Kevin P. Bui | LIS/Reporting | Leaders | 1 | US | No
Siddhant S. Dhar | LIS/Reporting | QA | 0.75 | US | Yes
Paul Q. Pham | LIS/Reporting | Developer | 1 | US | Yes
Anamika Rajput | LIS/Reporting | Developer | 1 | India | Yes
Srujana Nedunuri | LIS/Reporting | Developer | 1 | US | Yes
Pradnya N. Samnerkar | LIS/Reporting | BSA | 0.5 | US | Yes
Maria D. Ramos | Portal V1 | QA | 1 | US | Yes
Jorge Chuc Rivero | Portal V1 | QA | 1 | US | Yes
Lydia W. Kiragu | Portal V1 | BSA | 1 | US | Yes
Revathy Kovilpitchai | Portal V1 | Developer | 1 | US | Yes
Eric Werner | Portal V1 | Developer | 1 | US | Yes
Akash Agarwal | Portal V1 | Developer | 1 | India | Yes
Rutik A. Bhosale | Portal V1 | Developer | 1 | India | Yes
Hrishikesh Ukarande | Portal V1 | Developer | 1 | India | Yes
Sayali T. Pushkar | Portal V1 | QA | 1 | India | Yes
Kalpesh Chavan | Portal V1 | QA | 1 | India | Yes
Abhishek H. Mhatre | Portal V2 | Developer | 1 | India | Yes
Abhishek Jadhav | Portal V2 | QA | 1 | India | Yes
Abhishek Khande | Portal V2 | Developer | 1 | India | Yes
Ajay Kumar | Portal V2 | Tech Lead | 0.5 | India | Yes
Arohi Rai | Portal V2 | BSA | 1 | India | Yes
Gouri Nanadikar | Portal V2 | Developer | 1 | India | Yes
Harleen Kaur | Portal V2 | Developer | 1 | India | Yes
Kailash H. Suthar | Portal V2 | Developer | 1 | India | Yes
Kaushik P. Pankhaniya | Portal V2 | Developer | 1 | India | Yes
Kaveri V. Buchche | Portal V2 | QA | 1 | India | Yes
Manas D. Pandit | Portal V2 | BSA | 1 | India | Yes
Mehul Pamale | Portal V2 | Developer | 1 | India | Yes
Minal Soni | Portal V2 | Developer | 1 | India | Yes
Navneet M. Vaishnav | Portal V2 | Developer | 1 | India | Yes
Nikita D. Muljie | Portal V2 | Developer | 1 | India | Yes
Nishant R. Dumbre | Portal V2 | BSA | 1 | India | Yes
Nita Shinde | Portal V2 | QA | 1 | India | Yes
Ojas Mutha | Portal V2 | Tech Lead | 0.5 | India | Yes
Pranita Pedukar | Portal V2 | Developer | 1 | India | Yes
Rajan T. Metaliya | Portal V2 | Developer | 1 | India | Yes
Rushikesh S. Mapari | Portal V2 | Developer | 1 | India | Yes
Sanket Sheelwant | Portal V2 | QA | 1 | India | Yes
Shaliesh Maruti | Portal V2 | Developer | 1 | India | Yes
Shashank Srivastava | Portal V2 | Developer | 1 | India | Yes
Shatakshi Mete | Portal V2 | BSA | 1 | India | Yes
Shubhangi M. Topale | Portal V2 | Tech Lead | 0.5 | India | Yes
Sourabh K. Khot | Portal V2 | Developer | 1 | India | Yes
Vedanshu Bokade | Portal V2 | QA | 1 | India | Yes
Hardik Polinati | Integrations | Developer | 1 | India | Yes
Anamika Anand | Integrations | Tech Lead | 0.5 | US | Yes
Fahad Naeem | Integrations | Developer | 1 | US | Yes
Aniruddha Ramane | Integrations | Developer | 1 | India | Yes
Prathamesh S. Khile | Integrations | Developer | 1 | India | Yes
Prathamesh Rajput | Integrations | Developer | 1 | India | Yes
Shobhit Anand | Integrations | QA | 1 | India | Yes

## Availability
📅 Availability
Enter actual available hours per person per month. 176 = full month, 0 = absent.
Name | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27
Katy Zarty | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kaitlyn E. Walton | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Justin Branch | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Priti Kothavale | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Rowin W. Cordon | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Arnold Parge | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kamal Joshi | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Aastha Sahu | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Vrushali Kapadner | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Tamika P. Jarmond | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Katrina Lee | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
David A. Buchanan | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Yali Ren | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Amey Dodal | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Hrishikesh Kadam | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Gurneet Singh | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Win T. Aung | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Subin K. Pillai | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Raviraj R. Ghare | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Suraj Wankhade | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Abhishek N. Bulbule | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Srushti S. Raut | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Francisco J. Martinez | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Sneha Patil | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Siddhant S. Dhar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Paul Q. Pham | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Anamika Rajput | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Srujana Nedunuri | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Pradnya N. Samnerkar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Maria D. Ramos | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Jorge Chuc Rivero | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Lydia W. Kiragu | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Revathy Kovilpitchai | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Eric Werner | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Akash Agarwal | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Rutik A. Bhosale | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Hrishikesh Ukarande | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Sayali T. Pushkar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kalpesh Chavan | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Abhishek H. Mhatre | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Abhishek Jadhav | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Abhishek Khande | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Ajay Kumar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Arohi Rai | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Gouri Nanadikar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Harleen Kaur | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kailash H. Suthar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kaushik P. Pankhaniya | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Kaveri V. Buchche | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Manas D. Pandit | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Mehul Pamale | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Minal Soni | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Navneet M. Vaishnav | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Nikita D. Muljie | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Nishant R. Dumbre | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Nita Shinde | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Ojas Mutha | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Pranita Pedukar | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Rajan T. Metaliya | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Rushikesh S. Mapari | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Sanket Sheelwant | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Shaliesh Maruti | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Shashank Srivastava | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Shatakshi Mete | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Shubhangi M. Topale | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Sourabh K. Khot | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Vedanshu Bokade | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Hardik Polinati | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Fahad Naeem | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Aniruddha Ramane | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Prathamesh S. Khile | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Prathamesh Rajput | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Shobhit Anand | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Pamela Bowman | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Yutaka Hitomi | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Rayonia T. Slater-Smith | 176 | 176 | 168 | 176 | 184 | 168 | 176 | 176 | 168 | 184 | 168 | 160
Greg J. Andresen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Assumptions
⚙️ Assumptions
Hours per FTE drives capacity. BAU % = time spent on maintenance, not available for projects.
Hours per FTE / Month | 160
POD | Role | BAU %
Portal V1 | Developer | 20%
Portal V1 | QA | 25%
Portal V1 | BSA | 15%
Portal V1 | Tech Lead | 10%
Portal V2 | Developer | 20%
Portal V2 | QA | 25%
Portal V2 | BSA | 15%
Portal V2 | Tech Lead | 10%
Integrations | Developer | 20%
Integrations | QA | 25%
Integrations | BSA | 15%
Integrations | Tech Lead | 10%
Accessioning | Developer | 20%
Accessioning | QA | 25%
Accessioning | BSA | 15%
Accessioning | Tech Lead | 10%
Epic | Developer | 20%
Epic | QA | 25%
Epic | BSA | 15%
Epic | Tech Lead | 10%
LIS/Reporting | Developer | 20%
LIS/Reporting | QA | 25%
LIS/Reporting | BSA | 15%
LIS/Reporting | Tech Lead | 10%
Enterprise Systems | Developer | 20%
Enterprise Systems | QA | 25%
Enterprise Systems | BSA | 15%
Enterprise Systems | Tech Lead | 10%

## Sizing
📐 Sizing & Complexity
T-shirt sizes → base hours. Role effort mix. POD complexity multipliers.
Size | Base Hours | Role | Effort Mix % | POD | Complexity Multiplier
XS | 150 | Developer | 0.6 | Portal V1 | 1
S | 350 | QA | 0.2 | Portal V2 | 1
S+ | 600 | BSA | 0.1 | Integrations | 1.4
M | 1000 | Tech Lead | 0.1 | Accessioning | 1.2
M+ | 1800 |  |  | Epic | 1.1
L | 3000 |  |  | LIS/Reporting | 1.15
L+ | 5000 |  |  | Enterprise Systems | 1.05
XL | 8000
XXL | 12000
XXXL | 18000
Mega | 25000
Program | 35000

## Effort Patterns
📈 Effort Patterns
Relative weight per period. Normalised over project duration — no need to sum to 1.
Pattern | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Flat | bar: W1 to W12
Ramp Up | 0.5 | 0.7 | 0.9 | 1.1 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1
Ramp Down | 1.2 | 1.2 | 1.1 | 0.9 | 0.7 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
Up/Down | 0.7 | 0.9 | 1.1 | 1.2 | 1.1 | 0.9 | 0.7 | 0.5 | 1 | 1 | 1 | 1
QA Late Peak | 0.4 | 0.6 | 0.8 | 1 | 1.2 | 1.4 | 1.2 | 1 | 0.8 | 0.6 | 0.4 | 0.4
Dev Ramp | 0.6 | 0.8 | 1 | 1.1 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1
BSA Early | 1.6 | 1.4 | 1.2 | 1 | 0.8 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Tech Lead Light | 1.2 | 1.1 | 1 | 0.9 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Middle Spike | 0.1 | 0.2 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0
Spike + Stabilize | 0.3 | 0.25 | 0.15 | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
End Spike | 0.05 | 0.1 | 0.15 | 0.2 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Short 3m Up/Down | 0.6 | 1.2 | 0.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Projects
📁 Projects
One row per project. Use M1–M12 for Start/End Month. Status must be 'Active' for demand to be calculated.
Project | Priority | Owner | Start Month | End Month | Duration (M) | Default Pattern | Status | Target Launch | Notes
Optimus Prime | P0 | DG | M1 | M2 | 2 | Flat | Active | Apr-26
sgNIPT JSON | P1 | BD | M1 | M12 | 12 | Ramp Up | Active | Jul-26 | Natera
Panel Upgrade | P1 | BD | M1 | M2 | 2 | Flat | Active | May-26 | Quest
Unlock Report Automation | P1 | BD | M3 | M4 | 2 | Flat | Active | Jul-26 | USVA
VA PGx HL7 Integration | P1 | BD | M1 | M12 | 12 | Ramp Up | Active | Nov-26 | USVA
GH PGx Integration | P1 | BD | M1 | M12 | 12 | Ramp Up | Active | Aug-26 | GH
Digital Order Triage | P1 | S2C | M1 | M2 | 2 | Ramp Up | Active | Aug-26
Intelligent Client & Provider Search | P2 | S2C | M3 | M4 | 2 | Flat | Active | Aug-26
Accessioning OCR Enablement | P1 | S2C | M1 | M12 | 12 | Ramp Up | Active | Sep-26
Unified Test Catalog | P2 | S2C | M5 | M6 | 2 | Flat | Active | Jan-27
Next-Gen Order Tracking | P2 | S2C | M1 | M12 | 12 | Ramp Up | Active | Dec-26
Salesforce Bi-Directional Data Sync | P1 | S2C | M1 | M12 | 12 | Ramp Up | Active | Sep-26
Automated Medical Records | P2 | S2C | M1 | M12 | 12 | Ramp Up | Active | Sep-26
VoB Optimization | P2 | S2C | M1 | M12 | 12 | Ramp Up | Active | Sep-26
Quadax Billing Integration | P2 | S2C | M1 | M12 | 12 | Ramp Up | Active | Feb-27
Portal V2 MVP | P0 | Digital Products | M1 | M2 | 2 | Flat | Active | May-26
Portal V2 Q2 Enhancements | P1 | Digital Products | M4 | M5 | 2 | Ramp Up | Active | Nov-26
Portal V2 AI Capabilities | P1 | Digital Products | M1 | M12 | 12 | Ramp Up | Active | Feb-27
Patient Digital Informed Consent | P2 | Services | M5 | M6 | 2 | BSA Early | Active | Nov-26
Pre-Test Patient Education Tool | P2 | Services | M4 | M5 | 2 | Ramp Up | Active | Feb-27
Kit Return Patient Reminders | P2 | Services | M4 | M5 | 2 | Flat | Active | Aug-26
Gene Coverage Search Tool | P3 | Services | M6 | M7 | 2 | Flat | Active | Nov-26
Comparator Report Optimization | P3 | Services | M7 | M8 | 2 | Flat | Active | Dec-26
New Targeted Testing Reports | P3 | Services | M10 | M11 | 2 | Flat | Active | Feb-27
Spanish Translation | P3 | Services | M8 | M9 | 2 | Flat | Active | Feb-27
EPIC 1H Compendium Update | P1 | Digital Products | M1 | M2 | 2 | BSA Early | Active | Jun-26
EPIC New Client Aura Integration | P2 | Digital Products | M1 | M12 | 12 | Ramp Up | Active | Oct-26
CARE Everywhere | P2 | Digital Products | M5 | M6 | 2 | Up/Down | Active | Dec-26
Data Sharing Project | P2 | BD | M1 | M12 | 12 | Ramp Up | Active | Jul-26 | Natera
HC JSON | P2 | BD | M1 | M12 | 12 | Ramp Up | Active | Jun-26 | Natera
Automatic Variant Reclassification | P2 | Services | M4 | M5 | 2 | Dev Ramp | Active | Oct-26
GeneMatch Provider Research Tool | P3 | Services | M7 | M8 | 2 | Flat | Active | Jan-27
Genomic New Born Screening | P2 | DG | M6 | M7 | 2 | Ramp Up | Active | Feb-27 | Sunshine
SMD Workflow Consolidation | P2 | S2C | M4 | M5 | 2 | Up/Down | Active | Nov-26
Salesforce Advanced Capabilities | P3 | S2C | M1 | M12 | 12 | Ramp Up | Active | Feb-27
Portal V2 Account Management | P1 | Digital Products | M2 | M3 | 2 | Ramp Up | Active | Oct-26
Portal V2 User Profile Management | P1 | Digital Products | M3 | M4 | 2 | Ramp Up | Active | Nov-26
Patient Portal | P1 | Digital Products | M4 | M5 | 2 | Up/Down | Active | Feb-27
Post-Test Genetic Counseling Workflow | P2 | Digital Products | M5 | M6 | 2 | Ramp Up | Active | Feb-27
Patient Identification and Risk | P2 | Digital Products | M6 | M7 | 2 | Ramp Up | Active | Feb-27
EPIC Upgrades | P2 | Digital Products | M1 | M12 | 12 | Ramp Up | Active | Sep-26
Lab Workflow Automation | P2 | Operations | M3 | M4 | 2 | Dev Ramp | Active | Nov-26
Sample Tracking Enhancement | P2 | Operations | M4 | M5 | 2 | Flat | Active | Dec-26
Provider Portal v3 | P2 | Digital Products | M5 | M6 | 2 | Ramp Up | Active | Feb-27
New CMS/Cyto Reports | P3 | Services | M6 | M7 | 2 | Flat | Active | Dec-26
New Biochemical Reports | P3 | Services | M7 | M8 | 2 | Flat | Active | Jan-27

## POD Planning
🎯 POD Planning
One row per Project + POD. 'POD Start Month' blank = use project start. 'POD Duration' blank = use project duration.
Project | POD | Size | Complexity | Pattern Override | POD Start Month | POD Duration (M) | Notes
Optimus Prime | Portal V1 | S+ | 1 | Flat
Optimus Prime | Accessioning | XS | 1 | Flat
sgNIPT JSON | Integrations | XXL | 1 | Flat
sgNIPT JSON | LIS/Reporting | XS | 1 | Flat
Panel Upgrade | Portal V1 | S+ | 1 | Flat
Unlock Report Automation | LIS/Reporting | S+ | 1 | Flat
Unlock Report Automation | Enterprise Systems | XS | 1 | Flat
VA PGx HL7 Integration | Integrations | Mega | 1 | Ramp Up
VA PGx HL7 Integration | LIS/Reporting | S+ | 1 | Ramp Up
GH PGx Integration | Integrations | XXL | 1 | Flat
Digital Order Triage | Enterprise Systems | M+ | 1 | Ramp Up
Digital Order Triage | Portal V1 | S+ | 1 | Ramp Up
Intelligent Client & Provider Search | Enterprise Systems | S+ | 1 | Flat
Intelligent Client & Provider Search | Portal V1 | XS | 1 | Flat
Accessioning OCR Enablement | Accessioning | XS | 1 | Ramp Up
Accessioning OCR Enablement | Integrations | M+ | 1 | Ramp Up
Unified Test Catalog | Portal V1 | M+ | 1 | Flat
Unified Test Catalog | Portal V2 | S+ | 1 | Flat
Unified Test Catalog | LIS/Reporting | XS | 1 | Flat
Next-Gen Order Tracking | Enterprise Systems | M+ | 1 | Up/Down
Next-Gen Order Tracking | Integrations | XXL | 1 | Up/Down
Salesforce Bi-Directional Data Sync | Integrations | Mega | 1 | Ramp Up
Salesforce Bi-Directional Data Sync | Enterprise Systems | S+ | 1 | Ramp Up
Automated Medical Records | Integrations | XXL | 1 | Flat
Automated Medical Records | LIS/Reporting | XS | 1 | Flat
VoB Optimization | Integrations | XXL | 1 | Flat
VoB Optimization | Enterprise Systems | XS | 1 | Flat
Quadax Billing Integration | Integrations | Mega | 1 | Flat
Quadax Billing Integration | Epic | S+ | 1 | Flat
Portal V2 MVP | Portal V2 | M+ | 1 | Flat
Portal V2 Q2 Enhancements | Portal V2 | M+ | 1 | Ramp Up
Portal V2 Q2 Enhancements | Portal V1 | S+ | 1 | Ramp Up
Portal V2 AI Capabilities | Portal V2 | M+ | 1 | Middle Spike
Portal V2 AI Capabilities | Integrations | L+ | 1 | Middle Spike
Patient Digital Informed Consent | Portal V2 | S+ | 1 | BSA Early
Patient Digital Informed Consent | Portal V1 | XS | 1 | BSA Early
Pre-Test Patient Education Tool | Portal V2 | M+ | 1 | Ramp Up
Pre-Test Patient Education Tool | Portal V1 | S+ | 1 | Ramp Up
Kit Return Patient Reminders | Portal V1 | S+ | 1 | Flat
Kit Return Patient Reminders | Portal V2 | XS | 1 | Flat
Gene Coverage Search Tool | LIS/Reporting | S+ | 1 | Flat
Gene Coverage Search Tool | Portal V2 | XS | 1 | Flat
Comparator Report Optimization | LIS/Reporting | S+ | 1 | Flat
New Targeted Testing Reports | LIS/Reporting | XS | 1 | Flat
New Targeted Testing Reports | Portal V2 | XS | 1 | Flat
Spanish Translation | Portal V1 | XS | 1 | Flat
Spanish Translation | Portal V2 | S+ | 1 | Flat
EPIC 1H Compendium Update | Epic | M+ | 1 | BSA Early
EPIC New Client Aura Integration | Epic | M+ | 1 | Ramp Up
EPIC New Client Aura Integration | Integrations | XXL | 1 | Ramp Up
CARE Everywhere | Epic | M+ | 1 | Up/Down
CARE Everywhere | Enterprise Systems | S+ | 1 | Up/Down
Data Sharing Project | Integrations | XXL | 1 | Flat
Data Sharing Project | LIS/Reporting | XS | 1 | Flat
HC JSON | Integrations | L+ | 1 | Flat
HC JSON | Portal V2 | XS | 1 | Flat
Automatic Variant Reclassification | Enterprise Systems | M+ | 1 | Dev Ramp
Automatic Variant Reclassification | Portal V2 | S+ | 1 | Dev Ramp
GeneMatch Provider Research Tool | Portal V2 | S+ | 1 | Flat
Genomic New Born Screening | Accessioning | XS | 1 | Ramp Up
Genomic New Born Screening | LIS/Reporting | S+ | 1 | Ramp Up
Genomic New Born Screening | Portal V2 | XS | 1 | Ramp Up
SMD Workflow Consolidation | Accessioning | S+ | 1 | Up/Down
SMD Workflow Consolidation | Enterprise Systems | XS | 1 | Up/Down
Salesforce Advanced Capabilities | Integrations | Mega | 1 | Ramp Up
Salesforce Advanced Capabilities | Enterprise Systems | S+ | 1 | Ramp Up
Salesforce Advanced Capabilities | Portal V2 | S+ | 1 | Ramp Up
Portal V2 Account Management | Portal V2 | M+ | 1 | Ramp Up
Portal V2 User Profile Management | Portal V2 | M+ | 1 | Ramp Up
Patient Portal | Portal V2 | M+ | 1 | Up/Down
Patient Portal | Portal V1 | S+ | 1 | Up/Down
Post-Test Genetic Counseling Workflow | Portal V2 | M+ | 1 | Ramp Up
Post-Test Genetic Counseling Workflow | LIS/Reporting | XS | 1 | Ramp Up
Patient Identification and Risk | Portal V2 | M+ | 1 | Ramp Up
Patient Identification and Risk | Accessioning | S+ | 1 | Ramp Up
EPIC Upgrades | Epic | M+ | 1 | Flat
EPIC Upgrades | Integrations | L+ | 1 | Flat
Lab Workflow Automation | Accessioning | XS | 1 | Dev Ramp
Lab Workflow Automation | Enterprise Systems | XS | 1 | Dev Ramp
Sample Tracking Enhancement | Accessioning | M+ | 1 | Flat
Sample Tracking Enhancement | Portal V1 | S+ | 1 | Flat
Provider Portal v3 | Portal V1 | M+ | 1 | Ramp Up
Provider Portal v3 | Portal V2 | M+ | 1 | Ramp Up
New CMS/Cyto Reports | LIS/Reporting | S+ | 1 | Flat
New Biochemical Reports | LIS/Reporting | S+ | 1 | Flat
New Biochemical Reports | Portal V2 | XS | 1 | Flat

## POD Splits
🔀 POD Splits
Permanent = always split (e.g. 50% Epic / 50% Integrations). Temporary = short-term loan for a specific period.
Name | Start Month | End Month | Override POD | Allocation % | Notes | Type
Greg J. Andresen | M1 | M12 | Integrations | 0.5 | 50% Epic (home) + 50% Integrations | Permanent
Katrina Lee | M1 | M12 | Accessioning | 0.5 | Split: 50% ES + 50% Accessioning | Permanent
Siddhant S. Dhar | M1 | M12 | LIS/Reporting | 0.75 | 75% LIS/Reporting allocation | Permanent
Akash Agarwal | M3 | M4 | Portal V2 | 0.5 | 50% support while still on Portal V1 | Temporary
Hardik Polinati | M2 | M3 | Portal V2 | 0.4 | Temporary portal integration support | Temporary